## SE103 Team4
名稱 | Best Case Effort | Most Likely Effort | Worst Case Effort | Expected Effort | SD | VAR | Total VAR | 12.3346
Existing project comparison | 3 | 9 | 6 | 7.5 | 1.3043 | 1.7013 | Total Expected Effort | 130.75
Android SpeechRecognizer | 9 | 15 | 9 | 13 | 0 | 0 | Percentage Confident | 0.75
CMU Sphinx | 12 | 15 | 15 | 14.5 | 1.3043 | 1.7013 | Devisor | 2.3 | // 0.75 => 1.15 * 2
Others | 1.5 | 9 | 3 | 6.75 | 0.65217 | 0.42533 | Percentage Confident Effort | 134.7889
Android programming | 12 | 21 | 15 | 18.5 | 1.3043 | 1.7013 | Z(0.375) | 1.15
Extract requirement | 3 | 9 | 3 | 7 | 0 | 0
Set goal | 1.5 | 3 | 1.5 | 2.5 | 0 | 0
Define charactor | 1.5 | 3 | 1.5 | 2.5 | 0 | 0
Write creator use case | 1.5 | 3 | 3 | 2.75 | 0.65217 | 0.42533
Write participant use case | 1.5 | 3 | 3 | 2.75 | 0.65217 | 0.42533
Write talking use case | 1.5 | 3 | 3 | 2.75 | 0.65217 | 0.42533
Write receiving use case | 1.5 | 3 | 3 | 2.75 | 0.65217 | 0.42533
Write requirement document | 6 | 15 | 9 | 12.5 | 1.3043 | 1.7013
Server part architecture | 9 | 18 | 12 | 15.5 | 1.3043 | 1.7013
Client part architecture | 15 | 21 | 18 | 19.5 | 1.3043 | 1.7013

## Term Project WBS
名稱 | Best Case Effort | Most Likely Effort | Worst Case Effort | Expected Effort | SD | VAR | Total VAR | 77.888
Scope Definition | 12 | 16 | 20 | 16 | 3.4783 | 12.0983 | Total Expected Effort | 852
WBS | 1 | 3 | 5 | 3 | 1.7391 | 3.0246 | Percentage Confident | 0.75
Risk Analysis | 4 | 6 | 8 | 6 | 1.7391 | 3.0246 | Devisor | 2.3 | // 0.75 => 1.15 * 2
Technical Training | 4 | 6 | 8 | 6 | 1.7391 | 3.0246 | Percentage Confident Effort | 904.185
PEP Documentation | 4 | 10 | 12 | 10 | 3.4783 | 12.0983
Prepare Exisiting Survey of Java Compiler & APIs | 2 | 3 | 5 | 4 | 1.3043 | 1.7013
Java Compiler Survey | 6 | 8 | 30 | 12 | 10.4348 | 108.8847
Java Compiler API Survey | 3 | 5 | 10 | 6 | 3.0435 | 9.2628
Compiler Tree API Survey | 1 | 3 | 10 | 4 | 3.913 | 15.3119
Prepare Extension Introduction | 2 | 4 | 6 | 4 | 1.7391 | 3.0246
Bug Reproducing | 1 | 3 | 5 | 3 | 1.7391 | 3.0246
NullPointerException Bug | 3 | 5 | 20 | 8 | 7.3913 | 54.6314
Directory-too-deep Bug | 5 | 10 | 22 | 12 | 7.3913 | 54.6314
Java Compiler | 4 | 6 | 10 | 7 | 2.6087 | 6.8053
Java Compiler API | 5 | 7 | 12 | 8 | 3.0435 | 9.2628
Compiler Tree API | 3 | 4 | 8 | 5 | 2.1739 | 4.7259
CAMRL | 4 | 6 | 12 | 7 | 3.4783 | 12.0983
Extended Hitz | 1 | 2 | 5 | 3 | 1.7391 | 3.0246
Gephi | 5 | 8 | 12 | 9 | 3.0435 | 9.2628
Code Parser | 1 | 3 | 5 | 3 | 1.7391 | 3.0246
Java Compiler | 3 | 5 | 8 | 6 | 2.1739 | 4.7259
Java Compiler API | 1 | 2 | 3 | 2 | 0.86957 | 0.75614
Compiler Tree API | 1 | 1 | 3 | 2 | 0.86957 | 0.75614
CAMRL | 2 | 4 | 5 | 4 | 1.3043 | 1.7013
Extended Hitz | 1 | 2 | 5 | 3 | 1.7391 | 3.0246
Gephi | 3 | 8 | 12 | 8 | 3.913 | 15.3119
Code Parser | 1 | 3 | 5 | 3 | 1.7391 | 3.0246
Java Compiler | 1 | 2 | 4 | 3 | 1.3043 | 1.7013
Java Compiler API | 2 | 3 | 5 | 4 | 1.3043 | 1.7013
Compiler Tree API | 1 | 2 | 5 | 3 | 1.7391 | 3.0246
CAMRL | 2 | 3 | 5 | 4 | 1.3043 | 1.7013
Extended Hitz | 1 | 2 | 5 | 3 | 1.7391 | 3.0246
Gephi | 5 | 8 | 10 | 8 | 2.1739 | 4.7259
Code Parser | 2 | 4 | 6 | 3 | 1.7391 | 3.0246
Java Compiler | 10 | 30 | 50 | 30 | 17.3913 | 302.4575
Java Compiler API | 3 | 8 | 15 | 9 | 5.2174 | 27.2212
Compiler Tree API | 1 | 2 | 5 | 3 | 1.7391 | 3.0246
Extension (CAMRL, Extended Hitz, Gephi) | 20 | 22 | 60 | 28 | 17.3913 | 302.4575
Integration | 3 | 4 | 6 | 5 | 1.3043 | 1.7013
Java Compiler | 3 | 4 | 6 | 5 | 1.3043 | 1.7013
Java Compiler API | 2 | 3 | 5 | 4 | 1.3043 | 1.7013
Compiler Tree API | 1 | 2 | 5 | 3 | 1.7391 | 3.0246
CAMRL | 2 | 3 | 5 | 4 | 1.3043 | 1.7013
Extended Hitz | 2 | 5 | 10 | 6 | 3.4783 | 12.0983
Gephi | 5 | 10 | 15 | 10 | 4.3478 | 18.9036
Code Parser | 1 | 3 | 5 | 3 | 1.7391 | 3.0246
Traceability Matrices Development | 4 | 6 | 8 | 6 | 1.7391 | 3.0246
SRS Documentation | 40 | 60 | 100 | 64 | 26.087 | 680.5293
Presentation Slides | 4 | 8 | 20 | 10 | 6.9565 | 48.3932
CAMRL Redesign | 16 | 32 | 40 | 31 | 10.4348 | 108.8847
Extended Hitz Redesign | 24 | 32 | 48 | 34 | 10.4348 | 108.8847
Gephi Design | 10 | 15 | 18 | 15 | 3.4783 | 12.0983
Code Parser Redesign | 24 | 32 | 48 | 34 | 10.4348 | 108.8847
[M5] Redesign Review | 20 | 24 | 28 | 24 | 3.4783 | 12.0983
SDD Documentation | 24 | 36 | 48 | 36 | 10.4348 | 108.8847
CAMRL Implementation | 8 | 12 | 24 | 14 | 6.9565 | 48.3932
CAMRL Unit Test | 4 | 8 | 12 | 8 | 3.4783 | 12.0983
Extended Hitz Implementation | 16 | 24 | 32 | 24 | 6.9565 | 48.3932
Extended Hitz Unit Test | 8 | 12 | 16 | 12 | 3.4783 | 12.0983
Gephi Implementation | 6 | 8 | 10 | 8 | 1.7391 | 3.0246
Gephi Unit Test | 2 | 3 | 5 | 4 | 1.3043 | 1.7013
Code Parser Implementation | 24 | 56 | 112 | 58 | 38.2609 | 1463.8941
Code Parser Unit Test | 16 | 56 | 112 | 56 | 41.7391 | 1742.155
System Integration | 16 | 32 | 48 | 32 | 13.913 | 193.5728
Test Plan Development | 32 | 48 | 64 | 48 | 13.913 | 193.5728
Integration Test | 8 | 16 | 24 | 16 | 6.9565 | 48.3932
System Test | 8 | 16 | 24 | 16 | 6.9565 | 48.3932