## 工作表1
Item | Responsibility | Percentage Completed | Best Case (man day) | Most Likely Case (man day) | Worst Case (man day) | Expected Case | Actual Effort | Standard Deviation | Variance | Sum of Expected Case | Total Standard Deviation
[10 empty] | 192.0833 | 164.5652
[12 empty] | Total VAR | 1309.121
IP camera live transfer (Vedio) Design | Ray | 100% | 8 | 15 | 22 | 15 | 14 | 13.0435 | 170.1323 |  |  | Total Expected Effort | 192.0833
IP camera live transfer (Vedio) Implement | Ray | 60% | 2 | 4 | 6 | 4 |  | 3.4783 | 12.0983 |  |  | Percentage Confident | 0.75
IP camera live transfer (Vedio) Test | Ray | 0% | 2 | 3 | 7 | 3.5 |  | 3.913 | 15.3119 |  |  | Devisor | 2.3
Connect Arduino board and our middleware | Ray | 0% | 14 | 21 | 28 | 21 |  | 18.2609 | 333.4594 |  |  | Percentage Confident Effort | 233.6924
Speed up the data exchange from/to VM | Ray | 0% | 3 | 5 | 7 | 5 |  | 4.3478 | 18.9036 |  |  | Z(0.375) | 1.15
Microphone live transfer (Audio) | Ray | 0% | 4 | 7 | 10 | 7 |  | 6.087 | 37.051 |  |  | Last row number | 75
Network congestion experiment | Ray | 0% | 2 | 4.5 | 7 | 4.5 |  | 3.913 | 15.3119
Compile system architecture of CEP | Ray | 0% | 4 | 10 | 14 | 9.6667 |  | 7.8261 | 61.2476
Draw class diagram of CEP | Ray | 0% | 6 | 12 | 14 | 11.3333 |  | 8.6957 | 75.6144
Implement CEP | Ray | 0% | 2 | 5 | 7 | 4.8333 |  | 3.913 | 15.3119
Compile Velocity Engine System architecture | Ray | 0% | 2 | 3.5 | 5 | 3.5 |  | 3.0435 | 9.2628
Velocity engine code study | Ray | 0% | 5 | 9.5 | 14 | 9.5 |  | 8.2609 | 68.242
Compile system architecture of velocity engine | Ray | 0% | 1 | 3 | 5 | 3 |  | 2.6087 | 6.8053
Draw class diagram of velocity engine | Ray | 0% | 5 | 9.5 | 14 | 9.5 |  | 8.2609 | 68.242
Implement velocity engine | Ray | 0% | 2 | 6 | 10 | 6 |  | 5.2174 | 27.2212
Compile the domain knowledge of parsing API or data sheet | Ray | 0% | 7 | 20 | 28 | 19.1667 |  | 15.2174 | 231.569
Survey Docker | Chih Hsien | 100%
Change SDD to DDD | Chih Hsien | 100%
Implement IP camera motion jpeg adapter | Chih Hsien | 100%
Implement IP camera h.264/mpeg4 adapter | Chih Hsien | 100%
Fix virtual machine bug | Chih Hsien | 100%
Survey non-ip camera | Chih Hsien |  | 1 | 2 | 4 | 2.1667 |  | 2.1739 | 4.7259
Device hot plugging | Chih Hsien |  | 2 | 4 | 6 | 4 |  | 3.4783 | 12.0983
Survey wifi searching on linux | Chih Hsien | 100% | 0.5 | 1 | 1.5 | 1 | 0.5 | 0.86957 | 0.75614
Design and implement wifi searching | Chih Hsien | 100% | 0.5 | 1 | 1.5 | 1 | 1.5 | 0.86957 | 0.75614
Intergrate ncap and interoperation gateway in a better way | Chih Hsien | 50% | 1 | 2 | 2.5 | 1.9167 |  | 1.5217 | 2.3157
Revise velocity engine to adopt new design of adapter | Chih Hsien |  | 1 | 1.5 | 2 | 1.5 |  | 1.3043 | 1.7013
Let our gateway access arduino sensors | Chih Hsien |  | 2 | 3 | 4 | 3 |  | 2.6087 | 6.8053
Port interoperation code to ZyXEL gateway | Chih Hsien |  | 2 | 4 | 6 | 4 |  | 3.4783 | 12.0983
Survey Intel IoT DevKit, purchase the Grove Starter Kit | Mars | 100% |  |  |  | 0 |  | 0 | 0
Survey Arduino SDK | Mars | 100% |  |  |  | 0 |  | 0 | 0
Survey Intel Smart Gateway | Mars | 100% |  |  |  | 0 |  | 0 | 0
Survey Dropcam | Mars | 100% |  |  |  | 0 |  | 0 | 0
Survey D-Link mydlink | Mars | 100% |  |  |  | 0 |  | 0 | 0
Survey Intel IOT SDK | Mars | 100% |  |  |  | 0 |  | 0 | 0
Survey Qualcomm AllJoyn | Mars | 100% |  |  |  | 0 |  | 0 | 0
Survey IEEE 1905 | Mars | 100% |  |  |  | 0 |  | 0 | 0
Study Arduino | Mars | 100% | 3 | 5 | 7 | 5 |  | 4.3478 | 18.9036
Find and buy AllJoyn product and study libraries | Mars | 100% | 4 | 5 | 6 | 5 | 6 | 4.3478 | 18.9036
Write AllJoyn service and client | Mars | 90% | 3 | 4 | 5 | 4 |  | 3.4783 | 12.0983
Port AllJoyn application to gateway | Mars |  | 3 | 4 | 5 | 4 |  | 3.4783 | 12.0983
Integrate Connector pattern into Interoperation App's class diagram. | Uiling Hsu | 100% |  |  |  | 0 |  | 0 | 0
Study broadcast techniques. | Uiling Hsu | 100% |  |  |  | 0 |  | 0 | 0
Implement Class Diagram of the Mobile App. | Uiling Hsu | 100% |  |  |  | 0 |  | 0 | 0
Redesign the Interoperation App. | Uiling Hsu | 100% |  |  |  | 0 |  | 0 | 0
Implement the Interoperation App. | Uiling Hsu | 100% |  |  |  | 0 |  | 0 | 0
Add the UDP connection for image transfer | Uiling Hsu | 100% |  |  |  | 0 |  | 0 | 0
Test on csie sub-network | Uiling Hsu, Ray Chin | 100% |  |  |  | 0 |  | 0 | 0
Test Coverage of Interoperation APP | Uiling Hsu | 100% |  |  |  | 0 |  | 0 | 0
Use Object pool to conserve resource | Uiling Hsu | 100% |  |  |  | 0 |  | 0 | 0
Add the functionality on Interoperation App to choose specific gateway in a multi-gateway environment. | Uiling Hsu | 100% |  |  |  | 0 |  | 0 | 0
Study the Android Multimedia Framework. | Uiling Hsu | 100% |  |  |  | 0 |  | 0 | 0
Redesign the Interoperation App to adopt the Android Multimedia Framework. | Uiling Hsu | 100% |  |  |  | 0 |  | 0 | 0
Implement the connection and image display in Interoperation App | Uiling Hsu | 100% |  |  |  | 0 |  | 0 | 0
Testing interoperation App | Uiling Hsu | 100% |  |  |  | 0 |  | 0 | 0
Survey Skyhook SDK | Uiling Hsu |  | 1 | 2 | 3 | 2 |  | 1.7391 | 3.0246
Implement pool for display view in App | Uiling Hsu | 100% |  |  |  | 0 |  | 0 | 0
Implement pool for thread in App | Uiling Hsu |  | 1 | 2 | 3 | 2 |  | 1.7391 | 3.0246
Survey how to restream the video by gateway | Uiling Hsu, Ray Chin | 100% |  |  |  | 0 |  | 0 | 0
Survey how to extract the RTP from RTSP client | Uiling | 100% |  |  |  | 0 |  | 0 | 0
Survey how to decode media format from a stream of rtp | Uiling | 100% |  |  |  | 0 |  | 0 | 0
Survey how to decode media format from a stream of rtp | Uiling Hsu | 100% |  |  |  | 0 |  | 0 | 0
Study how open source project to depacketize RTP packet and decode the raw data to h.264 | Uiling Hsu | 100% |  |  |  | 0 |  | 0 | 0
Fix multi-gateway display on interoperation App | Uiling Hsu | 10% | 1 | 3 | 5 | 3 |  | 2.6087 | 6.8053
Add RTP packet processing and raw data decoding design in current design of interoperation App | Uiling Hsu | 100% | 2 | 3 | 4 | 3 |  | 2.6087 | 6.8053
Implement the new design of interoperation APP | Uiling Hsu | 100% | 2 | 3 | 4 | 3 |  | 2.6087 | 6.8053
Add SDP parsing | Uiling Hsu | 100% | 2 | 3 | 4 | 3 | 2 | 2.6087 | 6.8053
Testing the new design of interoperation APP | Uiling Hsu | 0% | 2 | 3 | 4 | 3 |  | 2.6087 | 6.8053
Add Descrbe State to our protocal | Uiling Hsu | 100% | 1 | 1 | 1 | 1 | 1 | 0.86957 | 0.75614
Add State Pattern to IP camera Streaming control Handler | Uiling Hsu | 100% | 1 | 2 | 3 | 2 | 2 | 1.7391 | 3.0246
TOTAL |  | 0% | 0 | 0 | 0 | 0 |  |  |  | Percentage Confidence | Total Estimation (Days)
[10 empty] | 0.75 | 303.0809